## Forward Traceability
Requirements | Tests | Executions | Defects
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-24 - Verify if we can sign in to Luma using Facebook Icon | GUI testing - FAIL | TMT2-25 - Backlog - When we try to login with Facebook in the window that opens, an error message appears: "App not active...."
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-26 - Verify if we can sign in to Luma using LinkedIn Icon | GUI testing - FAIL | TMT2-28 - Backlog - When we try to login with LinkedIn in the window that opens, an error message appears: "The application is disabled"
TMT2-23 - Testing the HTML element's | TMT2-29 - Verify if we can sign in to Luma using Yahoo! Icon | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-30 - Verify if we can sign in to Luma using GitHub Icon | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-32 - Veriffy if we can select a product from the list and add it to the shoping cart | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-33 - We check if by selecting a size the application page does not change. | GUI testing - FAIL | TMT2-34 - Backlog - After selecting the desired size, one or more images of the product were added.
TMT2-23 - Testing the HTML element's | TMT2-37 - We check if we can change the ordered quantity. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-38 - We check if, by changing the ordered quantity, the amount to be paid is also correctly changed. | GUI testing - FAIL | TMT2-39 - Backlog - After we changed the quantity, the delivery fee increased by $5 per piece.
TMT2-23 - Testing the HTML element's | TMT2-40 - We check if the order was placed successfully. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-41 - We check if the arrangement of images, buttons and texts on the page is appropriate. | GUI testing - FAIL | TMT2-42 - Backlog - Not all products have presentation images.
TMT2-23 - Testing the HTML element's | TMT2-43 - We check if the comparison button works properly. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-44 - We check if we can find products according to certain criteria (Shopping options) | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-45 - We check if we can add a review to a product. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-46 - We check if we can change the e-mail address corresponding to the account. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-47 - We check if we can successfully change the account password. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-48 - We check if we can search for a certain category of products. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's | TMT2-49 - We check if we can sort the products according to price, name or relevance. | GUI testing - PASS | None
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-50 - We check if we can change the delivery address before placing an order. | GUI testing - PASS | TMT2-51 - Backlog - The check box for the "Save in adress bock" overlaps with the text.
TMT2-23 - Testing the HTML element's - 1 defect | TMT2-52 - We check if we can change the billing address. | GUI testing - FAIL | TMT2-53 - Backlog - We don't have a button to save the new billing address.
TMT2-10 - Testing if a user can create an account and login into Luma. - 1 defect | TMT2-11 - Verify if we can create a new account for Luma | Functional testing - PASS | TMT2-31 - Backlog - During the testing of Magento 2 Luma application we've encountered 2 different forms for the Create an account.
TMT2-10 - Testing if a user can create an account and login into Luma. - 1 defect | TMT2-12 - Verify if we can log into Luma home page with valid credentials | Functional testing - FAIL | TMT2-14 - Backlog - After successfully logging in, the user was redirected to the "My Account" page of the app instead of being redirected to the main page.
TMT2-10 - Testing if a user can create an account and login into Luma. | TMT2-13 - Verify if we cann't log into Luma with invalid credentials home page | Functional testing - PASS | None
TMT2-10 - Testing if a user can create an account and login into Luma. | TMT2-15 - We check if we can create a new account using special characters in the "First name" fields on the "Create new account" page. | Functional testing - PASS | None
TMT2-10 - Testing if a user can create an account and login into Luma. | TMT2-16 - We check if we can create a new account using special characters in the "Last name" fields on the "Create new account" page. | Functional testing - PASS | None
TMT2-10 - Testing if a user can create an account and login into Luma. - 1 defect | TMT2-17 - We check if we we we can create a new account using numbers in the "First name/Last name" fields on the "Create new account" page. | Functional testing - FAIL | TMT2-18 - Backlog - The account has been created successfully if we enter letters and numbers in the "First name and/or Last name" fields on the "Create new account" page and we have been redirected to the main page of the application.
TMT2-10 - Testing if a user can create an account and login into Luma. | TMT2-19 - We check if we can use an e-mail that does not meet the requirements in the "Create new account" page. | Functional testing - PASS | None
TMT2-10 - Testing if a user can create an account and login into Luma. | TMT2-20 - We check if we can use a password that does not meet the requirements in the "Create new account" page. | Functional testing - PASS | None
TMT2-10 - Testing if a user can create an account and login into Luma. - 1 defect | TMT2-21 - We check if we can use an invalid phone number in the "Phone Number" field on the "Create new account" page. | Functional testing - FAIL | TMT2-22 - Backlog - Even though the "Phone number" field is a required field, the application created a new account using an invalid phone number.
TMT2-4 - Compayibility testing of Magento 2 Luma | TMT2-5 - Testing the compatibility of Magento 2 Luma with the latest version of Google Chrome | Compatibility testing - PASS | None
TMT2-4 - Compayibility testing of Magento 2 Luma | TMT2-6 - Testing the compatibility of Magento 2 Luma with the latest version of Mozila Firefox | Compatibility testing - PASS | None
TMT2-4 - Compayibility testing of Magento 2 Luma | TMT2-8 - Testing the compatibility of Magento 2 Luma with the latest version of Microsoft Edge | Compatibility testing - PASS | None
TMT2-2 - Magento 2 Luma theme - Frontend | None | None | None