## Issues
issuekey | Summary | TestStep | Test Data | Test Result | Status Category Changed | Parent | Fix versions | Resolution | Last Viewed | Root cause | Workaround | Time to resolution | Time to first response | Time to close after resolution | Time to review normal change | Priority | Labels | Remaining Estimate | Σ Original Estimate | Affects versions | Linked Issues | Assignee | Assignee-account-id | Status | Components | Responders | Severity | Affected hardware | Planned start | Planned end | Implementation plan | Backout plan | Test plan | Source | Investigation reason | Major incident | Σ Remaining Estimate | Creator | Creator-account-id | Sub-tasks | Request participants | Satisfaction | Satisfaction date | Approvals | Reporter | Request language | Σ Progress | Urgency | Affected services | Pending reason | Approver groups | Work category | Progress | Votes | Issue Type | Time Spent | Total forms | Project | Category | Σ Time Spent | Atlas project key | Atlas project status | Locked forms | Open forms | Submitted forms | Resolved | Work Ratio | Watchers | Created | Sprint | Flagged | Target start | Target end | [CHART] Date of First Response | [CHART] Time in Status | Story point estimate | Issue color | Parent Link | Rank | Updated | Original estimate | Description | Request Type | Epic Link | Start date | Change type | Change risk | Change reason | Security Level | Actual start | Actual end | Team | Organizations | Approvers | Impact | Environment | Due date
TMT2-54 | We check if we can change the shipping methods. | Acces the shopping cart |  |  | 2024-02-10T20:49:06.984+0200 | [10 empty] | Medium |  |  |  |  | TMT2-55 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T20:49:06.495+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qi7: | 2024-02-10T21:06:04.495+0200 |  | Preconditions: We have at least a product in our shopping cart. |  | TMT2-1
Press the "Procced to checkout" button
|  | In the "Shipping methods" section select other option |  | The shipping methods has changed successfully.
TMT2-52 | We check if we can change the billing address. | Acces the shopping cart |  |  | 2024-02-10T20:38:44.084+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-53 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T20:38:43.560+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qhr: | 2024-02-10T21:06:04.520+0200 |  | Preconditions: We have at least a product in our shopping cart. |  | TMT2-1
Press the "Procced to checkout" button
In the "Biling adress" section select "New adress"
Complete all the required fields
|  | Check the box "Save in adress Book" |  | The new billing address has been successfully saved.
TMT2-50 | We check if we can change the delivery address before placing an order. | Acces the shopping cart |  |  | 2024-02-10T20:16:25.839+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-51 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T20:16:25.301+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qh3: | 2024-02-10T20:33:25.367+0200 |  | Preconditions: We have at least a product in our shopping cart. |  | TMT2-1
Press the "Procced to checkout" button
In the "Shipping adress" section press "Edit" button
Complete all the required fields
Check the box "Save in adress bock"
|  | Press "Ship Here" button |  | The changes made will be saved.
TMT2-49 | We check if we can sort the products according to price, name or relevance. | Search for a category of products |  |  | 2024-02-10T19:59:48.625+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:59:47.988+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qgv: | 2024-02-10T19:59:48.660+0200 |  | Preconditions: N/A |  | TMT2-1
|  | Select a sorting criteria (Name, Price, Relevance) |  | The products will be displayed on the page according to the sorting criteria.
TMT2-48 | We check if we can search for a certain category of products. | Acces the Luma's home page |  |  | 2024-02-10T19:52:54.020+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:52:53.431+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qgn: | 2024-02-10T19:55:29.879+0200 |  | Preconditions: N/A |  | TMT2-1
Write a product category in the search box.
|  | Press "Enter" |  | The searched product category will be displayed on the page.
TMT2-47 | We check if we can successfully change the account password. | Sign in your account |  |  | 2024-02-10T19:39:07.723+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:39:07.256+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qgf: | 2024-02-10T19:39:07.770+0200 |  | Preconditions: We have a valid account. |  | TMT2-1
Acces the "My account" page
Press "Edit" button
Check the "Change Password" field
Complete the "Current password" field
Complet the "New password" field
Complete the "Confirm password" field
|  | Press "Save" button |  | The password will be successfuly changed.
TMT2-46 | We check if we can change the e-mail address corresponding to the account. | Sign in your account |  |  | 2024-02-10T19:31:34.684+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:31:34.142+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qg7: | 2024-02-10T21:02:26.693+0200 |  | Preconditions: We have a valid account. |  | TMT2-1
|  | Acces the "My account" page | https://osc-ultimate-demo.mageplaza.com/customer/account/
Press "Edit" button
Check the "Change Email" field
Change the e-mail adress
Complete the password field
|  | Press "Save" button |  | The e-mail adress will be successfuly changed.
TMT2-45 | We check if we can add a review to a product. | On the product page press the "Review" button. |  |  | 2024-02-10T19:23:36.090+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:23:35.674+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qfz: | 2024-02-10T19:23:36.121+0200 |  | Preconditions: Select a product. |  | TMT2-1
Complete all the fields.
|  | Press the "Submit Review" button |  | We receive a message telling us that our review has been successfully registered.
TMT2-44 | We check if we can find products according to certain criteria (Shopping options) | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-10T19:11:35.010+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:11:34.311+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qfr: | 2024-02-10T19:11:35.054+0200 |  | Preconditions: N/A |  | TMT2-1
Select a desidered category of products
|  | Enter the desired search criteria |  | The page will display the products that correspond to the chosen criteria.
TMT2-43 | We check if the comparison button works properly. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-10T19:05:21.768+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T19:05:21.397+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qfj: | 2024-02-10T19:05:21.805+0200 |  | Preconditions: N/A
Select the category of products
Select the products for comparison
|  | Press the "Compare" button |  | A new page will open with details about the products being compared.
TMT2-41 | We check if the arrangement of images, buttons and texts on the page is appropriate. | Acces the Home page of Magento 2 Luma | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-10T18:49:05.067+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-42 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T18:49:04.400+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qf3: | 2024-02-10T18:54:01.652+0200 |  | Preconditions; N/A |  | TMT2-1
|  | We check if the arrangement of images, buttons and texts on the page is appropriate. |  | All images, buttons and texts are arranged accordingly. All products also have presentation images.
TMT2-40 | We check if the order was placed successfully. | Complete the required fields |  |  | 2024-02-10T18:40:03.378+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T18:40:03.020+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qev: | 2024-02-10T18:41:29.476+0200 |  | Preconditions: The desidered products and quantity are selected.
|  | Press "Place order" button |  | The order has been placed successfully.
TMT2-38 | We check if, by changing the ordered quantity, the amount to be paid is also correctly changed. | Select the desidered size |  |  | 2024-02-10T18:07:17.227+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-39 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T18:07:16.681+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qef: | 2024-02-10T18:26:22.448+0200 |  | Preconditions: The desidered product is selected. |  | TMT2-1
Select the desidered Colour
Add the product into the shoping cart
Acces the shoping cart
|  | Change the ordered products quantity |  | The payment amount for the order has changed correctly.
TMT2-37 | We check if we can change the ordered quantity. | Select the desidered size |  |  | 2024-02-10T18:01:25.535+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T18:01:25.212+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qe7: | 2024-02-10T18:07:45.471+0200 |  | Preconditions: We have selected a product. |  | TMT2-1
Select the desidered colour
Add the product to the shoping cart
|  | Change the ordered quantity |  | The ordered quantity has been changed successfully.
TMT2-35 | We check if by selecting the colour the application page does not change. | Select the desidered colour |  | The application page does not change. | 2024-02-10T17:48:53.448+0200 | [10 empty] | Medium |  |  |  |  | TMT2-33,TMT2-36 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T17:48:53.058+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qdr: | 2024-02-10T18:07:52.696+0200 |  | Preconditions: The desired product has been selected |  | TMT2-1
TMT2-33 | We check if by selecting a size the application page does not change. | Select the desidered size |  | The application page does not change. | 2024-02-10T17:36:46.225+0200 | [10 empty] | Medium |  |  |  |  | TMT2-35,TMT2-23,TMT2-34 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T17:36:45.859+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qdb: | 2024-02-10T18:08:20.201+0200 |  | Preconditions: The desired product has been selected |  | TMT2-1
TMT2-32 | Veriffy if we can select a product from the list and add it to the shoping cart | Log in into luma | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-10T17:24:10.628+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T17:24:10.228+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qd3: | 2024-02-10T18:08:25.946+0200 |  | Preconditions: We are loged into Luma |  | TMT2-1
Select a product from the page
|  | Select the suitable size | Required field
|  | Select the color | Required field even if it is only one color
|  | Add the product into the shopingcart |  | The product was added successfuly into the shopingcart
TMT2-30 | Verify if we can sign in to Luma using GitHub Icon | Acces the Login page on Luma | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-02-10T16:43:25.822+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T16:43:25.308+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qcn: | 2024-02-10T16:49:17.630+0200 |  | Preconditions: We have acces to Luma Sign in page |  | TMT2-1
|  | Press the "Signin with GitHub" button |  | The link will send us to a new window where we will be able to log in to Luma with GitHub credentials.
TMT2-29 | Verify if we can sign in to Luma using Yahoo! Icon | Acces the Login page on Luma | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-02-10T16:34:50.891+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T16:34:50.399+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qcf: | 2024-02-10T16:49:09.565+0200 |  | Preconditions: We have acces to Luma Sign in page |  | TMT2-1
|  | Press the "Signin with Yahoo!" button |  | The link will send us to a new window where we will be able to log in to Luma with Yahoo! credentials.
TMT2-26 | Verify if we can sign in to Luma using LinkedIn Icon | Acces the Login page on Luma | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-02-10T16:25:19.992+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-28 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T16:25:19.518+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00qbz: | 2024-02-10T16:48:09.544+0200 |  | Preconditions: We have acces to Luma Sign in page |  | TMT2-1
|  | Press the "Signin with LinkedIn" button |  | The link will send us to a new window where we will be able to log in to Luma with LinkedIn credentials.
TMT2-24 | Verify if we can sign in to Luma using Facebook Icon | Acces the Login page on Luma | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-02-10T15:56:26.121+0200 | [10 empty] | Medium |  |  |  |  | TMT2-23,TMT2-25 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-10T15:56:25.530+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00q9r: | 2024-02-10T16:26:28.435+0200 |  | Preconditions: N/A |  | TMT2-1
|  | Press the "Signin with Facebook" button |  | The link will send us to a new window where we will be able to log in to Luma with Facebook credentials.
TMT2-21 | We check if we can use an invalid phone number in the "Phone Number" field on the "Create new account" page. | Acces the "Create an account" page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T19:43:37.298+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10,TMT2-22 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T19:43:36.482+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00ou7: | 2024-02-15T18:33:34.181+0200 |  | Precondition: We can access the "Create a new account" page in the Luma application |  | TMT2-1
Fill all the required fields with valid values
In the Phone number fill "123" or an invalid phone number
|  | Press "Create an account" |  | The account shoudn't be created because the Phone number field is a requirement
TMT2-20 | We check if we can use a password that does not meet the requirements in the "Create new account" page. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T19:26:06.801+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T19:26:06.287+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00otz: | 2024-02-15T18:33:14.575+0200 |  | Precondition: We can access the "Create a new account" page in the Luma application |  | TMT2-1
Press the "Create an account" button
Fill the "Password" field with different numbers of letters
Fill the other fields with valid credentials
|  | Press the "Create an account" button |  | The account cannot be created and the following errors are generated: "Minimum length of this field must be equal or greater than 8 symbols. Leading and trailing spaces will be ignored." or "Minimum of different classes of characters in password is 3. Classes of characters: Lower Case, Upper Case, Digits, Special Characters."
TMT2-19 | We check if we can use an e-mail that does not meet the requirements in the "Create new account" page. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T18:52:13.210+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T18:52:12.755+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00otj: | 2024-02-15T18:32:53.686+0200 |  | Precondition: We can access the "Create a new account" page in the Luma application |  | TMT2-1
Press the "Create an account" button
Fill the "Email" field with an email adress without @ or a valid domain
Fill the other fields with valid credentials
|  | Press the "Create an account" button |  | The account could not be created and the system generates the error "Please enter a valid email address"
TMT2-17 | We check if we we we can create a new account using numbers in the "First name/Last name" fields on the "Create new account" page. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T18:36:21.171+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10,TMT2-18 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T18:36:20.620+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00osn: | 2024-02-15T18:30:31.166+0200 |  | Precondition: We have acces to "Create new account" page of Luma's application |  | TMT2-1
Press the "Create an account" button
Insert numbers in "First name/Last name" field
Fill the other fields with valid data
|  | Push "Create an account" button |  | The account could not be created and the system gives us the error "First/Last name is not valid"
TMT2-16 | We check if we can create a new account using special characters in the "Last name" fields on the "Create new account" page. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T18:15:04.943+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T18:15:04.549+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00os7: | 2024-02-15T18:31:53.505+0200 |  | Precondition: We have acces to "Create new account" page of Luma's application |  | TMT2-1
Press the "Create an account" button
Insert special caracters in "Last name" field
Fill the other fields with valid data
|  | Push "Create an account" button |  | The account could not be created and the system gives us the error "Last name is not valid"
TMT2-15 | We check if we can create a new account using special characters in the "First name" fields on the "Create new account" page. | Acces the Luma Home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-02-03T18:05:23.230+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-02-03T18:05:22.712+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00orr: | 2024-02-15T18:28:00.572+0200 |  | Precondition: We have acces to "Create new account" page of Luma's application |  | TMT2-1
Press the "Create an account" button
Insert special caracters in "First name" field
Fill the other fields with valid data
|  | Push "Create an account" button |  | The account could not be created and the system gives us the error "First name is not valid"
TMT2-13 | Verify if we cann't log into Luma with invalid credentials home page | Acces the "Sign in" page | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-01-28T17:36:30.263+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-28T17:36:29.752+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00npb: | 2024-02-15T18:25:59.358+0200 |  | Precondition: We have acces to Luma Sign in page |  | TMT2-1
Fill the required feelds with invalid credentials
|  | Press the "Sign in" button | We get an error message | We cann't log into Luma home page
TMT2-12 | Verify if we can log into Luma home page with valid credentials | Open the Luma login (Sign in) link | https://osc-ultimate-demo.mageplaza.com/customer/account/login/ |  | 2024-01-28T17:08:53.859+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10,TMT2-14 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-28T17:08:53.311+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00nov: | 2024-02-15T18:24:49.137+0200 |  | Precondition: We have acces to Luma Sign in page |  | TMT2-1
Fill the required feelds with the valid credentials
|  | Press the "Sign in" button |  | We'll be redirected to Luma home page
TMT2-11 | Verify if we can create a new account for Luma | Acces the Luma home page | https://osc-ultimate-demo.mageplaza.com/ |  | 2024-01-28T17:03:40.435+0200 | [10 empty] | Medium |  |  |  |  | TMT2-10,TMT2-31 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-28T17:03:39.678+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00non: | 2024-02-10T17:03:45.232+0200 |  | Precondition: We have acces to “Create new account” page of Luma’s application |  | TMT2-1
Press the "Create an account" option
Filling the required feelds
|  | Press the "Create an account" buton |  | The account is created
|  | Validate the account within the e-mail submitted. |  | The account is validated
TMT2-8 | Testing the compatibility of Magento 2 Luma with the latest version of Microsoft Edge | Open latest version of Microsoft Edge |  |  | 2024-01-27T21:49:23.118+0200 | [10 empty] | Medium |  |  |  |  | TMT2-4 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-27T21:49:22.591+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00niv: | 2024-02-22T19:47:28.237+0200 |  | Precondition: Latest version of Microsoft Edge Browser must be installed on the computer |  | TMT2-1
Insert Magento application link in the search engine
|  | Acces the Magento link |  | The Magento Home page will be opened
TMT2-6 | Testing the compatibility of Magento 2 Luma with the latest version of Mozila Firefox | Open latest version of Mozila Firefox |  |  | 2024-01-27T21:44:56.542+0200 | [10 empty] | Medium |  |  |  |  | TMT2-4 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-27T21:44:56.081+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00nin: | 2024-02-22T19:47:17.029+0200 |  | Precondition: Latest version of Mozila Firefox must be installed on the computer |  | TMT2-1
Insert Magento application link in search engine
|  | Acces the Magento application link |  | The Magento Home page will be opened
TMT2-5 | Testing the compatibility of Magento 2 Luma with the latest version of Google Chrome | Open the latest version of Google Chrome browser |  |  | 2024-01-27T21:22:48.006+0200 | [10 empty] | Medium |  |  |  |  | TMT2-4 |  |  | Backlog | [13 empty] | IT Factory | 712020:ac03dc4b-ffe6-4f35-ba83-41f3c30a3c67 | [5 empty] | IT Factory |  | 0 | [5 empty] | 0 | 0 | Test |  |  | TMTA21_MihaiDaneasa | [8 empty] | -1 | 1 | 2024-01-27T21:22:47.537+0200 | [8 empty] | The Parent Link is only available to Jira Premium users. | 0¦i00ni7: | 2024-02-22T19:47:05.732+0200 |  | Preconditions: Latest version of Google Chrome must be installed on the computer. |  | TMT2-1
Introduce the Magento application link in search engine
|  | Acces the Magento application |  | The Magento Home page will open